## Ballast_Option
Stage | Tank | Action | Delta_t | PumpRate_tph | Priority | Rationale
Stage 5_PreBallast | VOID3.S | FILL | 152.08 | 10 | 2 | Pre-ballast for critical RoRo stage (Gate-A/B compliance)
Stage 5_PreBallast | VOID3.P | FILL | 147.15 | 10 | 2 | Pre-ballast for critical RoRo stage (Gate-A/B compliance)
Stage 5_PreBallast | FWB2.S | FILL | 48.98 | 10 | 2 | Pre-ballast for critical RoRo stage (Gate-A/B compliance)
Stage 5_PreBallast | VOIDDB2.C | FILL | 49.09 | 10 | 2 | Pre-ballast for critical RoRo stage (Gate-A/B compliance)
Stage 5_PreBallast | FODB1.P | FILL | 13.77 | 10 | 2 | Pre-ballast for critical RoRo stage (Gate-A/B compliance)
Stage 5_PreBallast | FODB1.S | FILL | 13.77 | 10 | 2 | Pre-ballast for critical RoRo stage (Gate-A/B compliance)
Stage 5_PreBallast | FODB1.C | FILL | 10.94 | 10 | 2 | Pre-ballast for critical RoRo stage (Gate-A/B compliance)
Stage 5_PreBallast | FW1.P | FILL | 5.16 | 10 | 2 | Pre-ballast for critical RoRo stage (Gate-A/B compliance)
Stage 5_PreBallast | FW1.S | FILL | 5.16 | 10 | 2 | Pre-ballast for critical RoRo stage (Gate-A/B compliance)
Stage 5_PreBallast | VOIDDB4.S | FILL | 5.06 | 10 | 2 | Pre-ballast for critical RoRo stage (Gate-A/B compliance)
Stage 5_PreBallast | FW2.P | FILL | 3.92 | 10 | 2 | Pre-ballast for critical RoRo stage (Gate-A/B compliance)
Stage 5_PreBallast | FW2.S | FILL | 3.92 | 10 | 2 | Pre-ballast for critical RoRo stage (Gate-A/B compliance)
Stage 5_PreBallast | VOIDDB4.P | FILL | 2.32 | 10 | 2 | Pre-ballast for critical RoRo stage (Gate-A/B compliance)
Stage 6A_Critical (Opt C) | FWCARGO1.S | FILL | 148.35 | 150 | 1 | Critical RoRo stage: FILL for draft control
Stage 6A_Critical (Opt C) | FWCARGO2.P | FILL | 148.36 | 150 | 1 | Critical RoRo stage: FILL for draft control
Stage 6A_Critical (Opt C) | FWCARGO2.S | FILL | 148.36 | 150 | 1 | Critical RoRo stage: FILL for draft control
Stage 6A_Critical (Opt C) | FWCARGO1.P | FILL | 140.15 | 150 | 1 | Critical RoRo stage: FILL for draft control
Stage 6A_Critical (Opt C) | FWB2.S | DISCHARGE | -70.43 | 150 | 1 | Critical RoRo stage: DISCHARGE for draft control
Stage 6A_Critical (Opt C) | FWB1.P | DISCHARGE | -50.57 | 150 | 1 | Critical RoRo stage: DISCHARGE for draft control
Stage 6A_Critical (Opt C) | FWB1.S | DISCHARGE | -50.57 | 150 | 1 | Critical RoRo stage: DISCHARGE for draft control
Stage 6A_Critical (Opt C) | FWB2.P | DISCHARGE | -21.45 | 150 | 1 | Critical RoRo stage: DISCHARGE for draft control
Stage 6A_Critical (Opt C) | VOID3.P | FILL | 4.93 | 150 | 1 | Critical RoRo stage: FILL for draft control

## Ballast_Exec
Stage | Step | Tank | Action | Start_t | Target_t | Delta_t | Time_h | Pump_ID | PumpRate_tph | Valve_Lineup | Hold_Point | Draft_FWD | Draft_AFT | Trim_cm | UKC | Notes
Stage 5_PreBallast | 1 | VOID3.S | FILL | 0 | 152.08 | 152.08 | 15.21 | SHIP_PUMP_01 | 10 | V-VOID3S-FILL,V-VOID3S-INLET | Y | 2.2 | 2.7 | 32.6 | 8.95 | WARNING: cumulative time 15.2h exceeds daylight window 12h
Stage 5_PreBallast | 2 | VOID3.P | FILL | 0 | 147.15 | 147.15 | 14.71 | SHIP_PUMP_01 | 10 | V-VOID3P-FILL,V-VOID3P-INLET | Y | 2.2 | 2.7 | 32.6 | 8.95 | WARNING: cumulative time 29.9h exceeds daylight window 12h
Stage 5_PreBallast | 3 | VOIDDB2.C | FILL | 0 | 49.09 | 49.09 | 4.91 | SHIP_PUMP_01 | 10 | V-VOIDDB2C-FILL,V-VOIDDB2C-INLET | Y | 2.2 | 2.7 | 32.6 | 8.95 | WARNING: cumulative time 34.8h exceeds daylight window 12h
Stage 5_PreBallast | 4 | FWB2.S | FILL | 21.45 | 70.43 | 48.98 | 4.9 | SHIP_PUMP_01 | 10 | V-FWB2S-FILL,V-FWB2S-INLET | Y | 2.2 | 2.7 | 32.6 | 8.95 | WARNING: cumulative time 39.7h exceeds daylight window 12h
Stage 5_PreBallast | 5 | FODB1.P | FILL | 0 | 13.77 | 13.77 | 1.38 | SHIP_PUMP_01 | 10 | V-FODB1P-FILL,V-FODB1P-INLET | Y | 2.2 | 2.7 | 32.6 | 8.95 | WARNING: cumulative time 41.1h exceeds daylight window 12h
Stage 5_PreBallast | 6 | FODB1.S | FILL | 0 | 13.77 | 13.77 | 1.38 | SHIP_PUMP_01 | 10 | V-FODB1S-FILL,V-FODB1S-INLET | Y | 2.2 | 2.7 | 32.6 | 8.95 | WARNING: cumulative time 42.5h exceeds daylight window 12h
Stage 5_PreBallast | 7 | FODB1.C | FILL | 10.95 | 21.89 | 10.94 | 1.09 | SHIP_PUMP_01 | 10 | V-FODB1C-FILL,V-FODB1C-INLET | Y | 2.2 | 2.7 | 32.6 | 8.95 | WARNING: cumulative time 43.6h exceeds daylight window 12h
Stage 5_PreBallast | 8 | FW1.P | FILL | 18 | 23.16 | 5.16 | 0.52 | SHIP_PUMP_01 | 10 | V-FW1P-FILL,V-FW1P-INLET | Y | 2.2 | 2.7 | 32.6 | 8.95 | WARNING: cumulative time 44.1h exceeds daylight window 12h
Stage 5_PreBallast | 9 | FW1.S | FILL | 18 | 23.16 | 5.16 | 0.52 | SHIP_PUMP_01 | 10 | V-FW1S-FILL,V-FW1S-INLET | N | 2.2 | 2.7 | 32.6 | 8.95 | WARNING: cumulative time 44.6h exceeds daylight window 12h
Stage 5_PreBallast | 10 | VOIDDB4.S | FILL | 0 | 5.06 | 5.06 | 0.51 | SHIP_PUMP_01 | 10 | V-VOIDDB4S-FILL,V-VOIDDB4S-INLET | N | 2.2 | 2.7 | 32.6 | 8.95 | WARNING: cumulative time 45.1h exceeds daylight window 12h
Stage 5_PreBallast | 11 | FW2.P | FILL | 10 | 13.92 | 3.92 | 0.39 | SHIP_PUMP_01 | 10 | V-FW2P-FILL,V-FW2P-INLET | N | 2.2 | 2.7 | 32.6 | 8.95 | WARNING: cumulative time 45.5h exceeds daylight window 12h
Stage 5_PreBallast | 12 | FW2.S | FILL | 10 | 13.92 | 3.92 | 0.39 | SHIP_PUMP_01 | 10 | V-FW2S-FILL,V-FW2S-INLET | N | 2.2 | 2.7 | 32.6 | 8.95 | WARNING: cumulative time 45.9h exceeds daylight window 12h
Stage 5_PreBallast | 13 | VOIDDB4.P | FILL | 0 | 2.32 | 2.32 | 0.23 | SHIP_PUMP_01 | 10 | V-VOIDDB4P-FILL,V-VOIDDB4P-INLET | Y | 2.2 | 2.7 | 32.6 | 8.95 | WARNING: cumulative time 46.1h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 14 | FWCARGO2.P | FILL | 0 | 148.36 | 148.36 | 0.99 | SHORE_PUMP | 150 | V-FWCARGO2P-FILL,V-FWCARGO2P-INLET | Y | 2.14 | 2.64 | 72 | 9.01 | WARNING: cumulative time 47.1h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 15 | FWCARGO2.S | FILL | 0 | 148.36 | 148.36 | 0.99 | SHORE_PUMP | 150 | V-FWCARGO2S-FILL,V-FWCARGO2S-INLET | Y | 2.14 | 2.64 | 72 | 9.01 | WARNING: cumulative time 48.1h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 16 | FWCARGO1.S | FILL | 0 | 148.35 | 148.35 | 0.99 | SHORE_PUMP | 150 | V-FWCARGO1S-FILL,V-FWCARGO1S-INLET | Y | 2.14 | 2.64 | 72 | 9.01 | WARNING: cumulative time 49.1h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 17 | FWCARGO1.P | FILL | 0 | 140.15 | 140.15 | 0.93 | SHORE_PUMP | 150 | V-FWCARGO1P-FILL,V-FWCARGO1P-INLET | Y | 2.14 | 2.64 | 72 | 9.01 | WARNING: cumulative time 50.0h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 18 | FWB2.S | DISCHARGE | 70.43 | 0 | -70.43 | 0.47 | SHORE_PUMP | 150 | V-FWB2S-DISCHARGE,V-FWB2S-OUTLET | Y | 2.14 | 2.64 | 72 | 9.01 | WARNING: cumulative time 50.5h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 19 | FWB1.P | DISCHARGE | 50.57 | 0 | -50.57 | 0.34 | SHORE_PUMP | 150 | V-FWB1P-DISCHARGE,V-FWB1P-OUTLET | Y | 2.14 | 2.64 | 72 | 9.01 | WARNING: cumulative time 50.8h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 20 | FWB1.S | DISCHARGE | 50.57 | 0 | -50.57 | 0.34 | SHORE_PUMP | 150 | V-FWB1S-DISCHARGE,V-FWB1S-OUTLET | Y | 2.14 | 2.64 | 72 | 9.01 | WARNING: cumulative time 51.2h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 21 | FWB2.P | DISCHARGE | 21.45 | 0 | -21.45 | 0.14 | SHORE_PUMP | 150 | V-FWB2P-DISCHARGE,V-FWB2P-OUTLET | Y | 2.14 | 2.64 | 72 | 9.01 | WARNING: cumulative time 51.3h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 22 | VOID3.P | FILL | 147.15 | 152.08 | 4.93 | 0.03 | SHORE_PUMP | 150 | V-VOID3P-FILL,V-VOID3P-INLET | Y | 2.14 | 2.64 | 72 | 9.01 | WARNING: cumulative time 51.4h exceeds daylight window 12h

## Ballast_Sequence
Stage | Step | Tank | Action | Start_t | Delta_t | Target_t | Pump_ID | PumpRate_tph | Time_h | Valve_Lineup | Draft_FWD | Draft_AFT | Trim_cm | UKC | Hold_Point | Notes | Valve_Sequence | Valve_Notes
Stage 5_PreBallast | 1 | VOID3.S | FILL | 0 | 152.08 | 152.08 | SHIP_PUMP_01 | 10 | 15.21 | V-VOID3S-FILL,V-VOID3S-INLET | 2.2 | 2.7 | 32.6 | 8.95 | Y | WARNING: cumulative time 15.2h exceeds daylight window 12h
Stage 5_PreBallast | 2 | VOID3.P | FILL | 0 | 147.15 | 147.15 | SHIP_PUMP_01 | 10 | 14.71 | V-VOID3P-FILL,V-VOID3P-INLET | 2.2 | 2.7 | 32.6 | 8.95 | Y | WARNING: cumulative time 29.9h exceeds daylight window 12h
Stage 5_PreBallast | 3 | VOIDDB2.C | FILL | 0 | 49.09 | 49.09 | SHIP_PUMP_01 | 10 | 4.91 | V-VOIDDB2C-FILL,V-VOIDDB2C-INLET | 2.2 | 2.7 | 32.6 | 8.95 | Y | WARNING: cumulative time 34.8h exceeds daylight window 12h
Stage 5_PreBallast | 4 | FWB2.S | FILL | 21.45 | 48.98 | 70.43 | SHIP_PUMP_01 | 10 | 4.9 | V-FWB2S-FILL,V-FWB2S-INLET | 2.2 | 2.7 | 32.6 | 8.95 | Y | WARNING: cumulative time 39.7h exceeds daylight window 12h
Stage 5_PreBallast | 5 | FODB1.P | FILL | 0 | 13.77 | 13.77 | SHIP_PUMP_01 | 10 | 1.38 | V-FODB1P-FILL,V-FODB1P-INLET | 2.2 | 2.7 | 32.6 | 8.95 | Y | WARNING: cumulative time 41.1h exceeds daylight window 12h
Stage 5_PreBallast | 6 | FODB1.S | FILL | 0 | 13.77 | 13.77 | SHIP_PUMP_01 | 10 | 1.38 | V-FODB1S-FILL,V-FODB1S-INLET | 2.2 | 2.7 | 32.6 | 8.95 | Y | WARNING: cumulative time 42.5h exceeds daylight window 12h
Stage 5_PreBallast | 7 | FODB1.C | FILL | 10.95 | 10.94 | 21.89 | SHIP_PUMP_01 | 10 | 1.09 | V-FODB1C-FILL,V-FODB1C-INLET | 2.2 | 2.7 | 32.6 | 8.95 | Y | WARNING: cumulative time 43.6h exceeds daylight window 12h
Stage 5_PreBallast | 8 | FW1.P | FILL | 18 | 5.16 | 23.16 | SHIP_PUMP_01 | 10 | 0.52 | V-FW1P-FILL,V-FW1P-INLET | 2.2 | 2.7 | 32.6 | 8.95 | Y | WARNING: cumulative time 44.1h exceeds daylight window 12h
Stage 5_PreBallast | 9 | FW1.S | FILL | 18 | 5.16 | 23.16 | SHIP_PUMP_01 | 10 | 0.52 | V-FW1S-FILL,V-FW1S-INLET | 2.2 | 2.7 | 32.6 | 8.95 | N | WARNING: cumulative time 44.6h exceeds daylight window 12h
Stage 5_PreBallast | 10 | VOIDDB4.S | FILL | 0 | 5.06 | 5.06 | SHIP_PUMP_01 | 10 | 0.51 | V-VOIDDB4S-FILL,V-VOIDDB4S-INLET | 2.2 | 2.7 | 32.6 | 8.95 | N | WARNING: cumulative time 45.1h exceeds daylight window 12h
Stage 5_PreBallast | 11 | FW2.P | FILL | 10 | 3.92 | 13.92 | SHIP_PUMP_01 | 10 | 0.39 | V-FW2P-FILL,V-FW2P-INLET | 2.2 | 2.7 | 32.6 | 8.95 | N | WARNING: cumulative time 45.5h exceeds daylight window 12h
Stage 5_PreBallast | 12 | FW2.S | FILL | 10 | 3.92 | 13.92 | SHIP_PUMP_01 | 10 | 0.39 | V-FW2S-FILL,V-FW2S-INLET | 2.2 | 2.7 | 32.6 | 8.95 | N | WARNING: cumulative time 45.9h exceeds daylight window 12h
Stage 5_PreBallast | 13 | VOIDDB4.P | FILL | 0 | 2.32 | 2.32 | SHIP_PUMP_01 | 10 | 0.23 | V-VOIDDB4P-FILL,V-VOIDDB4P-INLET | 2.2 | 2.7 | 32.6 | 8.95 | Y | WARNING: cumulative time 46.1h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 14 | FWCARGO2.P | FILL | 0 | 148.36 | 148.36 | SHORE_PUMP | 150 | 0.99 | V-FWCARGO2P-FILL,V-FWCARGO2P-INLET | 2.14 | 2.64 | 72 | 9.01 | Y | WARNING: cumulative time 47.1h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 15 | FWCARGO2.S | FILL | 0 | 148.36 | 148.36 | SHORE_PUMP | 150 | 0.99 | V-FWCARGO2S-FILL,V-FWCARGO2S-INLET | 2.14 | 2.64 | 72 | 9.01 | Y | WARNING: cumulative time 48.1h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 16 | FWCARGO1.S | FILL | 0 | 148.35 | 148.35 | SHORE_PUMP | 150 | 0.99 | V-FWCARGO1S-FILL,V-FWCARGO1S-INLET | 2.14 | 2.64 | 72 | 9.01 | Y | WARNING: cumulative time 49.1h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 17 | FWCARGO1.P | FILL | 0 | 140.15 | 140.15 | SHORE_PUMP | 150 | 0.93 | V-FWCARGO1P-FILL,V-FWCARGO1P-INLET | 2.14 | 2.64 | 72 | 9.01 | Y | WARNING: cumulative time 50.0h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 18 | FWB2.S | DISCHARGE | 70.43 | -70.43 | 0 | SHORE_PUMP | 150 | 0.47 | V-FWB2S-DISCHARGE,V-FWB2S-OUTLET | 2.14 | 2.64 | 72 | 9.01 | Y | WARNING: cumulative time 50.5h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 19 | FWB1.P | DISCHARGE | 50.57 | -50.57 | 0 | SHORE_PUMP | 150 | 0.34 | V-FWB1P-DISCHARGE,V-FWB1P-OUTLET | 2.14 | 2.64 | 72 | 9.01 | Y | WARNING: cumulative time 50.8h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 20 | FWB1.S | DISCHARGE | 50.57 | -50.57 | 0 | SHORE_PUMP | 150 | 0.34 | V-FWB1S-DISCHARGE,V-FWB1S-OUTLET | 2.14 | 2.64 | 72 | 9.01 | Y | WARNING: cumulative time 51.2h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 21 | FWB2.P | DISCHARGE | 21.45 | -21.45 | 0 | SHORE_PUMP | 150 | 0.14 | V-FWB2P-DISCHARGE,V-FWB2P-OUTLET | 2.14 | 2.64 | 72 | 9.01 | Y | WARNING: cumulative time 51.3h exceeds daylight window 12h
Stage 6A_Critical (Opt C) | 22 | VOID3.P | FILL | 147.15 | 4.93 | 152.08 | SHORE_PUMP | 150 | 0.03 | V-VOID3P-FILL,V-VOID3P-INLET | 2.14 | 2.64 | 72 | 9.01 | Y | WARNING: cumulative time 51.4h exceeds daylight window 12h