## 00_README
Workbook | Bryan Submission Data Pack (Template)
Version | v1.0
Created | 2025-12-30 17:54
Purpose | Provide a single SSOT-style input/calculation template for ballast operations submission.
How to use | 1) Fill blue cells only. 2) Keep SSOT_Master as single source. 3) Stage_Calc uses these inputs.
Key Sheets | 01_SSOT_Master, 07_Stage_Calc, 08_HoldPoint_Log, 09_Evidence_Log
Notes | Designed for AGI site operations.

## 01_SSOT_Master
Control / Input | Value | Unit | Notes | Owner | Source/Ref
SITE | AGI |  | AGI site operations | Logistics
Project / Shipment ID |  |  | Internal reference | Logistics
Vessel / LCT Name |  |  |  | Marine
Datum for Tide | CD |  | Chart Datum unless specified otherwise | Marine | Port tide table
Timezone | GST |  | Local timezone for logs | Marine
LBP | 60.30 | m | Length between perpendiculars | Marine | Vessel spec
Beam | 24.00 | m |  | Marine | Vessel spec
Molded Depth (D) | 3.65 | m | Used for freeboard estimate | Marine | Vessel spec
Lightship Displacement | 2800 | t | Baseline displacement (confirm) | Marine
Baseline Tmean | 2.00 | m | Baseline mean draft (confirm) | Marine
Gate-A: AFT Draft MIN | 2.70 | m | AFT >= this | Marine | Ops
Gate-B: FWD Draft MAX | 2.70 | m | FWD <= this (critical stages) | Marine | Ops
Gate-C: TRIM ABS MAX | 240 | cm | ABS(Trim_cm) <= this | Marine | Ops
UKC min | 0.50 | m | Under keel clearance minimum | Marine | Port
DepthRef (charted/berth) | 5.50 | m | Depth reference (same datum as tide) | Marine | Port
Squat | 0.00 | m | Allowance | Marine
Safety Allowance | 0.00 | m | Allowance | Marine
Pump rate (ship) | 10.0 | t/h | Default ship pump rate | Marine
Vent flow coeff | 0.86 | t/h/mm | Vent-limited effective rate | Marine
Ramp length | 8.30 | m | Ramp geometry | Marine
Linkspan height | 2.00 | m | Reference height | Marine

## 02_Vessel_Hydro
Hydro Table (input)
Fill hydrostatic points sorted by Displacement ascending. Minimum 2 points required.
# | Disp_t | Tmean_m | TPC_t/cm | MTC_t·m/cm | LCF_m | GM_m | Source/Remark
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60

## 03_Berth_Tide
Berth / Depth Reference (input)
DepthRef must use same datum as tide (e.g., CD).
Field | Value | Unit | Notes | Source
Site/Location |  |  | Berth/jetty identification
DepthRef | 5.50 | m | Use latest sounding if available
Datum | CD |  | e.g., CD
UKC min | 0.50 | m
Squat | 0.00 | m
Safety Allowance | 0.00 | m
Tide Forecast (input)
Fill official tide forecast (same datum).
DateTime | Tide_m | Source | Verified (Y/N) | Remarks

## 04_Cargo_SPMT
Cargo / SPMT Inputs (TR1/TR2 + SPMT)
Fill cargo weights and CoG. Provide stage position if variable.
Item | Weight_t | CoG_x_m | CoG_y_m | CoG_z_m | Final_Frame | Ramp_Frame | L_m | W_m | Remarks/Source
TR1 + SPMT |  |  |  |  | 42 | 17.95
TR2 + SPMT |  |  |  |  | 40 | 17.95
SPMT Self-weight (if separated)
Other / Dunnage / Lumber
Total cargo on LCT (TR1+TR2, excluding SPMT if separated) |  | t

## 05_Ballast_Tanks
Ballast Tank Catalog (input) | [10 empty] | VENT_COEFF (t/h/mm) | 0.86
List all relevant tanks and initial ROB. Use same tank names as in ballast solver. | [10 empty] | PUMP_RATE (t/h) default | 10
Tank | Side | Family | Capacity_t | Initial_ROB_t | Max_allow_t | x_m | Frame | PumpGroup | Vent_dia_mm | Remarks/Source
Stage-wise Tank Deltas (input per stage)
Fill delta (t) for each tank per stage. + = fill, - = discharge.
Tank | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | Stage 5_PreBallast | Stage 6A_Critical (Opt C) | Stage 6C | Stage 7 | Remarks

## 06_Stage_Plan
Stage_ID | Progress_% | Planned_Start | Planned_End | HoldPoint | GateB_Critical(Y/N) | Stage_Status | Remarks
Stage 1 | N/A |  |  | - | N | PLANNED | Arrival (lightship)
Stage 2 | N/A |  |  | Y | N | PLANNED | TR1 ramp start
Stage 3 | N/A |  |  | - | N | PLANNED | TR1 mid-ramp
Stage 4 | N/A |  |  | - | N | PLANNED | TR1 on deck
Stage 5 | N/A |  |  | - | N | PLANNED | TR1 final position
Stage 5_PreBallast | N/A |  |  | - | Y | PLANNED | Water supply complete (TR1 stowed)
Stage 6A_Critical (Opt C) | N/A |  |  | - | Y | PLANNED | TR2 ramp entry
Stage 6C | N/A |  |  | - | N | PLANNED | Final stowage
Stage 7 | N/A |  |  | - | N | PLANNED | Departure (cargo off)

## 07_Stage_Calc
Stage-wise Draft / Trim / Tide / Ramp Gates (submission table)
Parameter | Value | Unit | Notes
TOTAL_CARGO_T | 500 | t | TR1+TR2 total (edit)
GATE_AFT_MIN | 2.7 | m | AFT draft must be >= this
GATE_FWD_MAX | 2.7 | m | FWD draft must be <= this (critical stages)
TRIM_LIMIT_CM | 240 | cm | ABS(trim_cm) <= this
DEPTHREF_M | 5.5 | m | Berth depth reference (same datum as tide)
UKC_MIN_M | 0.5 | m | Under keel clearance minimum
SQUAT_M | 0 | m | Allowance
SAFETY_M | 0 | m | Allowance
Stage-wise Calculation Table
Stage_ID | HoldPoint | GateB_Critical | Stage_Remark | Progress_% | x_stage_m | W_stage_t | Displacement_t | Tmean_m | Trim_cm | Draft_FWD_m | Draft_AFT_m | Freeboard_min_m | Tide_required_m | Forecast_tide_m | Tide_margin_m | UKC_min_m | UKC_fwd_m | UKC_aft_m | Ramp_angle_deg | GM_m | Gate_FWD | Gate_AFT | Gate_TRIM | Gate_UKC | Gate_RAMP | HoldPoint_Band | Go/No-Go | Ballast_Action | Ballast_Time_h | Ballast_Net_t | Ballast_Alloc | Notes
Stage 1
Stage 2
Stage 3
Stage 4
Stage 5
Stage 5_PreBallast
Stage 6A_Critical (Opt C)
Stage 6C
Stage 7

## 08_HoldPoint_Log
Hold Point Measurement Log (Measured vs Predicted)
HP_GO_CM | 2 | cm | GO if max(¦Δ¦) <= this
HP_RECALC_CM | 4 | cm | RECALC if <= this else STOP
Time | Stage_ID | Meas_FWD_m | Meas_AFT_m | Meas_Trim_cm | Pred_FWD_m | Pred_AFT_m | ΔFWD_cm | ΔAFT_cm | ΔTrim_cm | Action | Comments

## 09_Evidence_Log
Site | Category | Document / Evidence Item | Req | Status | Due/Submitted | Portal | Ref No. | File/Link | Remarks
COMMON | Booking | Booking Confirmation | Y | PENDING |  | ATLP/MTG
COMMON | Insurance | Insurance Certificate | Y | PENDING |  | ATLP/MTG
COMMON | Manifest | Cargo Manifest | Y | PENDING |  | ATLP/MTG
COMMON | Contacts | Emergency Contact List | Y | PENDING |  | ATLP/MTG
AGI | Ramp | Ramp Angle Calculation | Y | PENDING |  | MTG
AGI | Berth | Berth Load Chart / Depth Confirmation | Y | PENDING |  | MTG
COMMON | Evidence | Hold Point Draft Photo (FWD/AFT) | Y | PENDING |  | ATLP/MTG

## 10_RACI
Activity / Deliverable | SCT Logistics | DSV/3PL | Vessel Master | Chief Officer/Ballast | Port Authority | HSE | Notes
Hydrostatic data pack + sign convention | A | C | R | R | I | I | Provide Hydro table and calculation method
Stage-wise plan + timeline | A | C | C | R | I | I | Include load transfer %, ballast sequence
Ballast tank list + initial ROB | C | I | I | R | I | I | Include pump/vent constraints
Tide forecast + depth confirmation | C | I | R | R | A | I | Use official source; align datum
HoldPoint measurement & decision | C | I | R | R | I | A | Record drafts/trim; decide GO/RECALC/STOP
ATLP/MTG submissions | R | C | I | I | A | C | Site-specific lead times
Photo/video evidence collection | A | C | I | I | I | R | Tag by stage/time/GPS
Final report & archive | A | C | C | R | I | C | 7-day submission requirement

## 11_Assumptions_Issues
ID | Type | Description | Value | Unit | Impact | Owner | Due | Status | Evidence/Ref
1 | Assumption | Hydro points provided are accurate and sorted by displacement |  |  | High | Marine |  | OPEN
2 | Assumption | DepthRef uses same datum as tide (CD) |  |  | High | Marine |  | OPEN
3 | Issue | Lightship displacement/draft not confirmed |  |  | Med | Marine |  | OPEN
4 | Gap | No clear explanation of draft mark positions |  |  | Med | Marine |  | OPEN

## 12_DataDictionary
Sheet | Field | Unit | Type | Definition / Rule
01_SSOT_Master | GATE_AFT_MIN_M | m | Input | Minimum aft draft allowed (AFT >=).
01_SSOT_Master | GATE_FWD_MAX_M | m | Input | Maximum forward draft allowed (FWD <=).
01_SSOT_Master | TRIM_LIMIT_CM | cm | Input | Absolute trim limit. Trim = (Daft - Dfwd)*100.
03_Berth_Tide | Tide_m | m | Input | Tide height above datum (e.g., CD).
04_Cargo_SPMT | Weight_t | t | Input | Cargo weight including SPMT if not separated.
05_Ballast_Tanks | Delta_t | t | Input | Per stage tank delta: + ballast, - discharge.
07_Stage_Calc | Trim_cm | cm | Calc | Trim = (Daft - Dfwd)*100.
07_Stage_Calc | Tide_required_m | m | Calc | Required tide so UKC >= UKC_MIN.
08_HoldPoint_Log | Action | - | Calc | GO/RECALC/STOP based on thresholds.

## Pack_A_Inputs_SSOT
Pack A: Inputs & Assumptions (SSOT)
1. Vessel / Show-stopper inputs
Parameter | Value | Unit | Source/Reference | Note
LBP (Length Between Perpendiculars) |  | m
Beam |  | m
Depth (D, molded) | 3.65 | m | Vessel spec
Lightship Displacement | 2800 | t | Vessel spec
Gate AFT MIN | 2.70 | m | Ops
Gate FWD MAX | 2.70 | m | Ops
Trim ABS limit | 240 | cm | Ops
UKC min | 0.50 | m | Port
DepthRef | 5.50 | m | Port

## Pack_B_Calculation_Formulas
Pack B: Calculation Sheet (Formula + Sign Convention)
(1) Draft / Trim (Hydro 기반)
Parameter/Formula | Formula/Definition | Unit/Note | Reference
Tmean (m) | T_mean = (D_fwd + D_aft) / 2
Delta Tmean (m) | Delta T_mean = Sum(Delta W) / (TPC * 100) | TPC: t/cm
Delta Trim (m) | Delta Trim = Sum(Delta W*(x-LCF)) / MTC | MTC: t·m/cm
Trim (cm) | Trim_cm = (D_aft - D_fwd) * 100
Sign: Trim | + = Aft deeper / - = Bow down
Sign: x | +Aft / -Fwd (midship ref)
(2) UKC / Tide Required
Item | Definition | Unit/Note | Reference
Depth_available | DepthRef + Forecast_Tide | m | 03_Berth_Tide
UKC | Depth_available - (Draft + Squat + Safety) | m
Tide_required | max(0, (Draft_max + Squat + Safety + UKC_min) - DepthRef) | m

## Pack_D_Tide_Window_RACI
Pack D: Tide Window & RACI
Stage-wise Tide Window
Stage | Required WL (m) | Forecast Tide (m) | Margin (m) | Window Time | Source
Stage 1
Stage 2
Stage 3
Stage 4
Stage 5
Stage 5_PreBallast
Stage 6A_Critical (Opt C)
Stage 6C
Stage 7
RACI Matrix (optional)